## Slide 1
Analysis of ACC CSR Monthly Progress Report Data
Quick Report
June 2017
Submitted on
12 July 2017
Access Dashboard at
https://datastudio.google.com/u/0/org//reporting/0B9KpuN-Luu2gZGd4cWJzV0xjUjQ/page/QM0E

## Slide 2
Planned
till June 2017
% Achieved
Achieved
till June 2017
Budget
(₹crore)
Leverage
(₹ crore)
Beneficiaries
( nos.)
Leverage Ratio
Cost/ Beneficiary
Planned
Jan-Dec 2017
% Achieved
Achieved
till June 2017
5.74
2.82
2,74,021
49%
209
9.32
7.38
4,08,672
79%
228
62%
38%
67%
ACC YTD [Jan – June 2017]
ACC YTY [Jan – Dec 2017]
5.74
2.82
2,74,021
49%
209
16.69
14.84
5,10,011
89%
327
34%
19%
54%
Source: ACC Plant MPR June, 2017
Key Indicators
(*) Note: YTY Planned data (for Jan-Dec) taken from MPR except for Jamul for which no planned data is available in MPR, ACC Business plan figures sued. There is also a mismatch between the MPR Plan data and the ACC Business Plan figures and needs to be reconciled.

## Slide 3
What is the Big Picture
Planned figures not met: 62% of the Planned Spend targets till June 2017 has been met. Shortfall of Expenditure by Rs. 3.58 crore(YTD).
High Pressure to Spend in 3rd &4th quarter: Of the yearly targets, only 34% has been achieved till date. 76% of the expenditure to be done in 3rd and 4th quarter.
Average Monthly Spend need Acceleration: The average monthly spending till May 2017 has been Rs. 95 lakhs/month. Going forward this has to be accelerated to Rs. 1.82 crore/month if the yearly target of 16. 69 crores is to be met
Leverage not keeping pace: Only 38% of the Planned leverage targets till June 2017 has been met. Shortfall in Leverage is by Rs. 4.56 crores (YTD).
Yearly Leverage Target Seem Unattainable: Of the yearly Planned Leverage targets, only 19% has been achieved till date.
Average Monthly Leverage Needs Big Push: The average monthly leverage till June 2017 has been Rs 47 lakhs/month. Going forward this has to be accelerated to Rs. 2.0 crore/month if the yearly target has to be achieved.
Beneficiary Target on Track: With 2.74 lakh beneficiary reached 64% of the YTD targets achieved.
Yearly Targets Achievement on Upward trend: 51% of YTY targets has been achieved as on date.
The possibility of double counting of beneficiaries has to be assessed

## Slide 4
What is the Big Picture
Leverage Ratio Can Do Better: Till the month of June, 49% of the Expenditure could be leveraged against the Planned target leverage ratio of 76%.
Yearly Targets too Ambitious to be Achieved: The Leverage ratio for the year is 96% against the achieved leverage ratio till date of 49%, achieving of which is a tall order.
Cost/Beneficiary Performance Good :The Cost/Beneficiary achieved is Rs 209 against Planned cost/beneficiary of Rs 327. This indicates in all probability all the capital expenditure items have not kicked in.

## Slide 5
Plantwise: Budget v/s Expenditure
LOW
AVERAGE
GOOD
OVER ACHIEVER
Plant | Budget (YTY) Jan-Dec 2017 | Budget (YTD) Jan-June 2017 | Expenditure (YTD) Jan-June 2017 | Achieved | 
 |  |  |  | YTY | YTD
Kymore | 15,160,000 | 8,760,000 | 2,687,085 | 18% | 31%
Tikaria | 16,879,315 | 11,896,858 | 4,068,894 | 24% | 34%
Kudithini | 7,576,500 | 5,143,800 | 2,328,590 | 31% | 45%
Bargarh | 18,042,017 | 10,245,017 | 4,768,338 | 26% | 47%
Chanda | 11,808,751 | 6,312,256 | 3,565,798 | 30% | 56%
Lakheri | 7,800,000 | 3,660,000 | 2,168,000 | 28% | 59%
Sindri | 18,858,998 | 8,114,019 | 4,976,836 | 26% | 61%
Damodhar | 3,779,520 | 2,378,348 | 1,589,470 | 42% | 67%
Gagal | 17,792,500 | 10,182,000 | 6,834,218 | 38% | 67%
Wadi | 9,755,000 | 4,022,500 | 2,977,500 | 31% | 74%
Madukkarai | 14,395,000 | 6,618,000 | 5,414,500 | 38% | 82%
Thondebhavi | 3,629,550 | 1,337,950 | 1,274,927 | 35% | 95%
Jamul | 10,691,141 | 8,751,141 | 8,847,141 | 83% | 101%
Chaibasa | 10,691,000 | 5,732,896 | 5,854,949 | 55% | 102%
Total | 166,859,292 | 93,154,785 | 57,356,246 | 34% | 62%

## Slide 6
Inference: Budget v/s Expenditure
Some Plants have Seriously Fallen Behind in Spending: Kymore, and Tikaria have only spend on an average 30% of their budget allocations on YTD basis as on June 2017. Kymore and Tikaria with budgets over a crore need to be closely monitored for spends if the overall ACC target are to be achieved.
Traditional Good Performers Returning Average Performance: Kudithini, Bargarh, Chanda and Lakheri are returning average performance with having spend 40-60% of their allotted budgets till June 2017. The spends need to be ramped up.
Over Achievers – A surprise Pack: Jamul and Chaibasa are the surprise pick having achieved more than the targeted spends.

## Slide 7
Sectorwise: Budget v/s Expenditure
LOW
AVERAGE
GOOD
Plant | Budget (YTY) Jan-Dec 2017 | Budget (YTD) Jan-June 2017 | Expenditure (YTD) Jan-June 2017 | Achieved | 
 |  |  |  | YTY | YTD
# Save Kids Life | 350,000 | 155,000 | 60,901 | 17% | 39%
S.Swacchata | 29,339,526 | 19,985,847 | 8,999,086 | 31% | 45%
Arogyam | 17,929,271 | 9,131,404 | 4,381,831 | 24% | 48%
Dhrona | 5,525,000 | 2,707,500 | 1,326,955 | 24% | 49%
NGO admin /others | 7,310,828 | 4,038,172 | 2,116,667 | 29% | 52%
S.Paryavaran | 21,485,494 | 13,112,000 | 7,761,879 | 36% | 59%
Leisa | 10,325,440 | 6,410,755 | 4,220,222 | 41% | 66%
Disha | 22,218,680 | 14,568,680 | 10,842,640 | 49% | 74%
Vidya Utkarsh | 32,740,704 | 13,135,760 | 9,842,567 | 30% | 75%
Swavlamban | 18,054,349 | 9,889,666 | 7,787,448 | 43% | 79%
Vidya Saarthi | 1,580,000 | 20,000 | 16,050 | 1% | 80%
Total | 166,859,292 | 93,154,784 | 57,356,246 | 34% | 62%

## Slide 8
Inference: Budget v/s Expenditure
Key Verticals Showing Low Spends: Important verticals like Sampoorn Swacchata and Arogyam have shown very poor spends averaging 30% of the planned budgets.
Three Sectors mainstay in Spending : Disha, Vidya Utkarsh and Swavlamban which constitute 50% of the total spending show good spending performance compared to the target.

## Slide 9
Budget Achievement (Vertical and Plant)
The Yellow boxes are sectors for which there is budget allocation but no expenditure has been initiated as on June 2017.
Null means there is no budget allocation.
 | # Save Kids Life | Arogyam | Dhrona | Disha | Leisa | NGO admin /others | S.Paryavaran | S.Swacchata | Swavlamban | Vidya Saarthi | Vidya Utkarsh
Kymore | 0% | 4.04% | 63.49% | 5.29% | 20.10% | 0.27% | 20.67% | 8.16% | 0% | 0% | 43.70%
Kudithini | null | 76.18% | 14.62% | 19.52% | 70.26% | 50% | 4.74% | 39.18% | 33.82% | 321% | 15.96%
Tikaria | null | 5.24% | 0% | null | 49.59% | 4.76% | 0% | 45.93% | 62.52% | null | 26.25%
Bargarh | 17.96% | 57.18% | 0% | 41.79% | null | 0% | 12.75% | 5.60% | 31.29% | null | 14.98%
Damodhar | null | 14.78% | 0% | null | 13.25% | 50% | 48.49% | 37.02% | 55.13% | null | null
Lakheri | null | 0% | 22.50% | 0% | 31.67% | null | 102.50% | 0% | 64% | null | 22.09%
Sindri | null | 25.12% | 0% | 48.89% | null | null | 12.39% | 12.50% | 62.51% | null | 3.40%
Chanda | null | 38.61% | null | 0% | 23.61% | null | null | 23.33% | 58.38% | null | 34.52%
Gagal | null | 69.99% | 23.04% | 0% | null | null | null | 43.72% | 36.99% | null | 32.02%
Jamul | null | null | null | 100% | null | null | 170.31% | 55.21% | null | null | 64.59%
Wadi | null | 26.82% | null | 42.82% | null | 150% | 0% | 0% | 0% | null | 23.25%
Madukkarai | 46% | null | 0% | 0% | 0% | 0% | null | null | 27.39% | null | 4.81%
Thondebhavi | null | 72% | 54.08% | 3.93% | null | 28.84% | 21.29% | 99.36% | 12.47% | null | 65.29%
Chaibasa | null | 14.95% | 0% | 36.48% | 110.82% | 32.34% | 93.33% | 62.96% | 69.96% | null | 53.45%

## Slide 10
Budget v/s Expenditure
Plants have failed to initiate Planned projects: A number of projects which were planned have not seen start of implementation (expenditure) despite budget allocation. This is alarming given half the year has passed by.
Kymore : #SaveKidsLives, Swavlamban, Vidyasaarthi
Tikaria: Drona, S.Paryavaran
Bargarh: Drona
Damodar: Drona
Lakheri: Arogyam, Disha, S Swacchata
Sindri: Drona,
Chanda & Gagal: Drona
Wadi : S. Paryavaran, S. Swacchata, Swavlamban
Madukkarai: Drona, Disha, Leisa
Chaibasa: Drona

## Slide 11
Leverage by Plant : Planned v/s Achieved
Plant | Leverage (YTY) Jan-Dec 2017 | Leverage(YTD) Jan-June 2017 | Leverage Realised (YTD) Jan-June 2017 | Achieved |  | leverage Ratio | 
 |  |  |  | YTY | YTD | Planned (YTY) | Achieved (YTD)
Tikaria | 10,842,000 | 7,413,500 | 214,950 | 2% | 3% | 54% | 5%
Gagal | 18,159,000 | 8,570,000 | 450,000 | 2% | 5% | 102% | 7%
Sindri | 18,875,000 | 7,252,150 | 608,650 | 3% | 8% | 100% | 12%
Kymore | 17,250,000 | 11,495,000 | 1,331,250 | 8% | 12% | 114% | 50%
Chaibasa | 14,829,000 | 9,607,496 | 1,625,740 | 11% | 17% | 139% | 28%
Bargarh | 2,430,500 | 1,430,000 | 511,800 | 21% | 36% | 13% | 11%
Chanda | 6,724,000 | 4,154,010 | 1,528,624 | 23% | 37% | 57% | 43%
Kudithini | 7,576,500 | 5,100,200 | 2,549,630 | 34% | 50% | 100% | 109%
Jamul | 6,380,000 | 5,780,000 | 3,980,000 | 62% | 69% | 60% | 45%
Damodhar | 5,391,500 | 2,690,748 | 2,542,415 | 47% | 94% | 143% | 160%
Lakheri | 7,000,000 | 3,000,000 | 3,185,000 | 46% | 106% | 90% | 147%
Wadi | 12,514,000 | 5,855,000 | 6,568,282 | 52% | 112% | 128% | 221%
Thondebhavi | 16,492,000 | 591,000 | 696,840 | 4% | 118% | 454% | 55%
Madukkarai | 3,940,000 | 870,000 | 2,400,000 | 61% | 276% | 27% | 44%
Total | 148,403,500 | 73,809,104 | 28,193,181 | 19% | 38% |  | 
LOW
AVERAGE
GOOD
Extraordinary

## Slide 12
Leverage by Plant : Planned v/s Achieved
Poor Leverage Performance (below 20% of planned YTD): Tikaria(3%), Gagal(5%), Sindri(8%), Kymore (12%), Chaibasa (17%). Big push needed.
Average Leverage Performance (20% to 50% of planned YTD) : Bargarh (36%), Chanda(37%), Kudithini( 50%).
Good Performers ( 50% to 75% YTD) : Jamul (67%)
Super Performers (75% and above YTD): Damodar (94%), Lakheri(106%), Wadi (112%), Thondebhavi(118%), Madukkarai (276%)

## Slide 13
Leverage by Sector : Planned v/s Achieved
Plant | Leverage (YTY) Jan-Dec 2017 | Leverage(YTD) Jan-June 2017 | Leverage Realised (YTD) Jan-June 2017 | Leverage Achieved |  | Leverage Ratio | 
 |  |  |  | YTY | YTD | YTY | YTD
NGO admin /others | 500,000 | 0 | 200,000 | 0% | 0% | 7% | 0%
S.Paryavaran | 7,400,000 | 325000 | 4,917,500 | 4% | 7% | 34% | 4%
S.Swacchata | 42,778,000 | 4230665 | 24,680,498 | 10% | 17% | 146% | 47%
Vidya Utkarsh | 7,634,000 | 1035240 | 5944996 | 14% | 17% | 23% | 11%
Leisa | 15,630,000 | 1847567 | 10,279,600 | 12% | 18% | 151% | 44%
# Save Kids Life | 159,500 | 16000 | 56000 | 10% | 29% | 46% | 26%
Dhrona | 3,385,000 | 782490 | 1,654,000 | 23% | 47% | 61% | 59%
Swavlamban | 44,060,000 | 9435593 | 13,230,210 | 21% | 71% | 244% | 121%
Disha | 10,876,000 | 4674500 | 5,993,000 | 43% | 78% | 49% | 43%
Arogyam | 15,481,000 | 5846126 | 6853300 | 38% | 85% | 86% | 133%
Vidya Saarthi | 500,000 | 0 | 0 | 0% | null | 32% | 0%
Total | 148,403,500 | 28,193,181 | 73,809,104 |  |  | 19% | 50%

## Slide 14
Poor Leverage Performance: S. Paryavaran (7%). S. Swachata(17%), Vidya Utkarsh(17%), LEISA (18%), # Savekidslife(29%)
Good Performance : Drona(47%), Swavlamban(71%), Disha(78%), Arogyam (85%)
Leverage by Sector : Planned v/s Achieved

## Slide 15
Beneficiary by Plant
LOW
AVERAGE
GOOD
OVER ACHIEVER
Plant | Target Beneficiary(YTY) | Target Beneficiary(YTD) | Actual Beneficiary(YTD) | Beneficiary Achieved |  | Cost/Beneficiary | 
 |  |  |  | (YTY) | (YTD) | (YTY) | (YTD)
Tikaria | 9,732 | 4,223 | 914 | 9% | 22% | 1,734 | 2,781
Kymore | 34,072 | 17,455 | 5,739 | 17% | 33% | 451 | 199
Damodhar | 12,828 | 7,481 | 3,800 | 30% | 51% | 295 | 266
Bargarh | 16,312 | 7,495 | 4,605 | 28% | 61% | 1,106 | 722
Kudithini | 21,455 | 15,770 | 11,889 | 55% | 75% | 353 | 88
Chaibasa | 24,142 | 10,318 | 7,899 | 33% | 77% | 443 | 656
Gagal | 39,141 | 26,214 | 21,783 | 56% | 83% | 455 | 266
Wadi | 6,638 | 2,570 | 2,201 | 33% | 83% | 1,470 | 1,198
Sindri | 24,301 | 12,660 | 13,354 | 55% | 105% | 776 | 264
Thondebhavi | 7,251 | 4,560 | 5,283 | 73% | 116% | 498 | 187
Jamul | 1,687 | 1,687 | 2,187 | 130% | 130% | 10,580 | 3,993
Lakheri | 7,002 | 4,540 | 6,706 | 96% | 148% | 1,114 | 272
Chanda | 10,679 | 3,944 | 5,996 | 56% | 152% | 1,106 | 546
Madukkarai | 272,560 | 100,980 | 155,999 | 57% | 154% | 53 | 24
Total | 487,800 | 219,897 | 248,355 |  |  |  | 

## Slide 16
Beneficiary
Majority of the Plants show high achievement in beneficiary coverage: Except for Tikaria( 22%) and Kymore(33%), the remaining Plants have performed well. 7 plants have returned average to good performance and 6 plants have over achieved (i.e. surpassed the YTD beneficiary targets)
Cost per beneficiary remains within estimates: Except for Tikaria and Chaibasa, the cost /beneficiary remains within budgeted limits for rest of the plants.

## Slide 17
Beneficiary by Sector
Vertical | Target Beneficiary(YTY) | Target Beneficiary(YTD) | Actual Beneficiary(YTD) | Beneficiary Achieved |  | Cost/Beneficiary | 
 |  |  |  | (YTY) | (YTD) | (YTY) | (YTD)
Leisa | 156,626 | 154,427 | 1,562 | 1% | 1% | 66 | 2,702
NGO admin /others | 1,367 | 1,049 | 56 | 4% | 5% | 5348 | 37798
# Save Kids Life | 3980 | 1470 | 490 | 12% | 33% | 88 | 124
Vidya Utkarsh | 49,851 | 34,927 | 13,928 | 28% | 40% | 657 | 707
Disha | 5,763 | 3,416 | 2,237 | 39% | 65% | 3855 | 4,847
S.Swacchata | 51,614 | 38,105 | 33,290 | 64% | 87% | 568 | 270
Swavlamban | 20,532 | 11,001 | 9,711 | 47% | 88% | 879 | 802
Dhrona | 10,428 | 6,734 | 6478 | 62% | 96% | 530 | 205
Arogyam | 84,863 | 43413 | 42421 | 50% | 98% | 211 | 103
S.Paryavaran | 124,885 | 114,130 | 163,875 | 131% | 144% | 172 | 47
Vidya Saarthi | 102 | 0 | 0 | 0% | null | 15490 | null
Total | 510011 | 408672 | 274048 |  |  |  | 

## Slide 18
Beneficiary
LEISA performance very poor: Only 1% of the budgeted beneficiaries has been achieved. This is because 1,50,000 beneficiaries targeted to benefit from removal of prosopis juliflora trees, the project not yet started.
Most Projects Performing well : Most of the projects are doing reasonably well in terms of beneficiary reached.

## Slide 19
Thank You
The MPR Dashboard is available at
https://datastudio.google.com/u/0/org//reporting/0B9KpuN-Luu2gZGd4cWJzV0xjUjQ/page/QM0E