## Slide 1
Analysis of ACC CSR Monthly Progress Report Data
Quick Report
May 2017
Submitted on
12 June 2017
Access Dashboard at
https://datastudio.google.com/u/0/org//reporting/0B9KpuN-Luu2gZGd4cWJzV0xjUjQ/page/QM0E

## Slide 2
Planned
till May 2017
% Achieved
Achieved
till May 2017
Budget
(₹crore)
Leverage
(₹ crore)
Beneficiaries
( nos.)
Leverage Ratio
Cost/ Beneficiary
Planned
Jan-Dec 2017
% Achieved
Achieved
till May 2017
4.48
2.32
2,48,297
52%
180
7.91
6.01
2,19,897
76%
360
57%
39%
113%
ACC YTD [Jan – May 2017]
ACC YTY [Jan – Dec 2017]
4.48
2.32
2,48,297
52%
180
17.42*
16.97
4,87,800
97%
357
26%
14%
51%
Source: ACC Plant MPR May, 2017
Key Indicators
(*) Note: YTY Planned data (for Jan-Dec) taken from MPR except for Jamul for which no planned data is available in MPR, ACC Business plan figures sued. There is also a mismatch between the MPR Plan data and the ACC Business Plan figures and needs to be reconciled.

## Slide 3
What is the Big Picture
Planned figures not met:
Only 57% of the Planned Spend targets till May 2017 has been met. There is a shortfall of Expenditure vis-a-vis Planned by Rs. 3.43 crore on YTD basis.
Of the yearly Planned targets, only 26% has been achieved till date. This will put significant spending pressure in the third and fourth quarter.
The average monthly spending till May 2017 has been Rs. 89.6 lakhs/month. Going forward this has to be accelerated to Rs. 1.85 crore/month if the yearly target has to be achieved.
Leverage not keeping pace:
Only 39% of the Planned leverage targets till May 2017 has been met. There is a shortfall in planned v/s achieved Leverage by Rs. 3.69 crores on YTD basis.
Of the yearly Planned Leverage targets, only 14% has been achieved till date.
The average monthly leverage till May 2017 has been Rs 46 lakhs/month. Going forward this has to be accelerated to Rs. 2.09 crore/month if the yearly target has to be achieved.
Beneficiary Target on Track:
With 2.48 lakh beneficiary reached it has surpassed the YTD target by 13%.
Of the total yearly target, 51% achieved as on date.
The possibility of double counting of beneficiaries has to be assessed

## Slide 4
What is the Big Picture
Leverage Ratio Reasonable Achievement
Till the month of May, 52% of the Expenditure could be leveraged against the Planned target leverage ratio of 76%
The Leverage ratio for the year is 96% against the achieved leverage ratio till date of 52%, necessitating ramping up of leverage performance
Cost/Beneficiary Performance Good
The Cost/Beneficiary achieved is Rs 180 against Planned cost/beneficiary of Rs 360

## Slide 5
Plant | Budget (YTY) Jan-Dec 2017 | Budget (YTD) Jan-May 2017 | Expenditure (YTD) Jan-May 2017 | Achieved | 
 |  |  |  | YTY | YTD
Kymore | 15,360,000 | 6,910,000 | 1,143,992 | 7% | 17%
Kudithini | 7,576,500 | 4,785,800 | 1,046,128 | 14% | 22%
Tikaria | 16,879,314 | 9,400,548 | 2,541,925 | 15% | 27%
Bargarh | 18,042,017 | 8,060,517 | 3,323,509 | 18% | 41%
Damodhar | 3,779,520 | 2,119,713 | 1,009,585 | 27% | 48%
Lakheri | 7,800,000 | 3,370,000 | 1,826,000 | 23% | 54%
Sindri | 18,858,998 | 6,450,134 | 3,527,995 | 19% | 55%
Chanda | 11,808,751 | 5,304,380 | 3,275,697 | 28% | 62%
Gagal | 17,792,500 | 8,122,500 | 5,783,865 | 33% | 71%
Jamul | 17,848,000 | 11,993,497 | 8,733,141 | 49% | 73%
Wadi | 9,755,000 | 3,139,500 | 2,637,000 | 27% | 84%
Madukkarai | 14,372,000 | 3,941,000 | 3,785,500 | 26% | 96%
Thondebhavi | 3,612,200 | 1,001,100 | 989,377 | 27% | 99%
Chaibasa | 10,691,000 | 4,502,730 | 5,179,949 | 48% | 115%
Total | 174,175,800 | 79,101,419 | 44,803,663 | 26% | 57%
Plantwise: Budget v/s Expenditure
LOW
AVERAGE
GOOD
OVER ACHIEVER

## Slide 6
Plant | Budget (YTY) Jan-Dec 2017 | Budget (YTD) Jan-May 2017 | Expenditure (YTD) Jan-May 2017 | Achieved | 
 |  |  |  | YTY | YTD
Vidya Saarthi | 3,380,000 | 770,000 | 16,050 | 0% | 2%
Dhrona | 5,973,004 | 2,305,835 | 881,000 | 15% | 38%
Vidya Utkarsh | 32,298,450 | 17,192,758 | 7,952,976 | 25% | 41%
NGO admin /others | 7,057,827 | 3,172,229 | 1,351,334 | 19% | 43%
Arogyam | 21,082,271 | 8,117,955 | 3,886,672 | 18% | 48%
# Save Kids Life | 350,000 | 125,000 | 60,901 | 17% | 49%
S.Paryavaran | 21,721,490 | 10,158,294 | 5,281,116 | 24% | 52%
Leisa | 10,325,440 | 5,145,272 | 3,092,643 | 30% | 60%
S.Swacchata | 29,627,969 | 13,098,640 | 7,040,584 | 24% | 69%
Disha | 22,628,000 | 11,155,596 | 9,028,310 | 40% | 71%
Swavlamban | 19,731,349 | 7,859,839 | 6,212,077 | 31% | 79%
Total | 174,175,800 | 79,101,418 | 44,803,663 | 26% | 57%
Sectorwise: Budget v/s Expenditure
LOW
AVERAGE
GOOD

## Slide 7
Budget v/s Expenditure (Vertical and Plant)
 | # Save Kids Life | Arogyam | Dhrona | Disha | Leisa | NGO admin /others | S.Paryavaran | S.Swacchata | Swavlamban | Vidya Saarthi | Vidya Utkarsh
Kymore | 0% | 11% | 0% | 18% | 22% | 2% | 14% | 3% | 0% | 0% | 34%
Kudithini | null | 84% | 101% | 28% | 62% | 100% | 0% | 1% | 54% | 321% | 128%
Tikaria | null | 12% | 0% | null | 40% | 4% | 0% | 55% | 57% | null | 39%
Bargarh | 45% | 77% | 0% | 45% | null | 0% | 27% | 0% | 52% | null | 57%
Damodhar | null | 28% | null | null | 20% | 100% | 0% | 66% | 115% | null | null
Lakheri | null | 0% | 60% | 0% | 46% | null | 118% | 0% | 110% | null | 93%
Sindri | null | 77% | 0% | 37% | null | null | 20% | 24% | 174% | null | 0%
Chanda | null | 112% | null | 0% | 35% | null | null | 46% | 100% | null | 159%
Gagal | null | 109% | 38% | null | null | null | null | 60% | 86% | null | 96%
Jamul | null | 0% | 0% | 99% | null | null | 63% | 84% | 0% | 0% | 97%
Wadi | null | 89% | null | 110% | null | 100% | 0% | 0% | 0% | null | 79%
Madukkarai | null | null | null | null | null | null | 96% | null | 103% | null | 100%
Thondebhavi | null | 72% | 100% | 100% | null | 102% | 105% | 99% | 103% | null | 95%
Chaibasa | null | 36% | null | 55% | 259% | 64% | 150% | 81% | 200% | null | 104%
The Yellow boxes are sectors for which there is budget allocation but no expenditure has been initiated as on May 2017.
Null means there is no budget allocation.

## Slide 8
Budget v/s Expenditure
Some Plants have Seriously Fallen Behind in Spending:
Kymore, Kudhithini and Tikaria have only spend on an average quarter of their budget allocations on YTD basis as on May 2017. Kymore and Tikaria with budgets over a crore need to be closely monitored for spends if the overall ACC target are to be achieved.
6 plants including Bargarh, Damodar, Lakheri, Sindri and Chanda are average performers having spend 40-60% of their allotted budgets till May 2017. The spends need to be ramped up.
Sectorwise Spending has significant variation:
Expenditure performance for for DISHA and Swavlamban have been satisfactory, for the remaining sectors the spending range from poor to average.
6 plants including Bargarh, Damodar, Lakheri, Sindri and Chanda are average performers having spend 40-60% of their allotted budgets till May 2017. The spends need to be ramped up.
Plants have failed to intiate Planned projects:
A number of projects which were planned have not seen start of implementtion (expenditure). This is alarming given half the year has passed by

## Slide 9
Leverage by Plant : Planned v/s Achieved
Plant | Leverage (YTY) Jan-Dec 2017 | Leverage (YTD) Jan-May 2017 | Leverage Realised (YTD) Jan-May 2017 | Achieved |  | leverage Ratio | 
 |  |  |  | YTY | YTD | Planned (YTY) | Achieved (YTD)
Chaibasa | 15,329,000 | 6,684,247 | 124,240 | 1% | 2% | 143% | 2%
Tikaria | 10,917,000 | 4,847,500 | 197,950 | 2% | 4% | 65% | 8%
Gagal | 18,159,000 | 5,845,000 | 375,000 | 2% | 6% | 102% | 6%
Sindri | 18,875,000 | 5,303,950 | 428,650 | 2% | 8% | 100% | 12%
Bargarh | 2,430,500 | 1,121,000 | 276,500 | 11% | 25% | 13% | 8%
Kymore | 17,250,000 | 8,245,000 | 2,207,757 | 13% | 27% | 112% | 193%
Chanda | 6,724,000 | 3,521,675 | 1,385,111 | 21% | 39% | 57% | 42%
Jamul | 27,100,000 | 9,915,004 | 3,980,000 | 15% | 40% | 152% | 46%
Kudithini | 7,576,500 | 3,891,700 | 2,128,043 | 28% | 55% | 100% | 203%
Lakheri | 7,000,000 | 2,800,000 | 2,400,000 | 34% | 86% | 90% | 131%
Damodhar | 5,391,500 | 2,242,290 | 2,093,957 | 39% | 93% | 143% | 207%
Thondebhavi | 16,492,000 | 556,000 | 586,840 | 4% | 106% | 457% | 59%
Wadi | 12,514,000 | 4,520,000 | 4,829,932 | 39% | 107% | 128% | 183%
Madukkarai | 3,940,000 | 600,000 | 2,200,000 | 56% | 367% | 27% | 58%
Total | 169,698,500 | 60,093,366 | 23,213,980 | 14% | 39% |  | 
LOW
GOOD
OVER ACHIEVER

## Slide 10
Plant | Leverage (YTY) Jan-Dec 2017 | Leverage (YTD) Jan-May 2017 | Leverage Realised (YTD) Jan-May 2017 | Leverage Achieved |  | Leverage Ratio | 
 |  |  |  | YTY | YTD | YTY | YTD
# Save Kids Life | 159,500 | 48500 | 0 | 0% | 0% | 46% | 0%
NGO admin /others | 500,000 | 100000 | 0 | 0% | 0% | 7% | 0%
S.Paryavaran | 7,416,667 | 3431667 | 175,000 | 2% | 5% | 34% | 3%
Leisa | 15,630,000 | 8868000 | 1,347,967 | 9% | 15% | 151% | 44%
Vidya Utkarsh | 7,817,333 | 5874998 | 914,947 | 12% | 16% | 24% | 12%
S.Swacchata | 58,798,000 | 21036249 | 3,567,332 | 6% | 17% | 198% | 51%
Dhrona | 3,385,000 | 1246000 | 429,890 | 13% | 35% | 57% | 49%
Arogyam | 18,481,000 | 6257692 | 3,894,676 | 21% | 62% | 88% | 100%
Disha | 11,876,000 | 3823000 | 3,473,000 | 29% | 91% | 52% | 38%
Swavlamban | 45,135,000 | 9407260 | 9,411,168 | 21% | 100% | 229% | 151%
Vidya Saarthi | 500,000 | 0 | 0 | 0% | null | 15% | 0%
Total | 169,698,500 | 60,093,366 | 23,213,980 |  |  | 14% | 39%
Leverage by Sector : Planned v/s Achieved

## Slide 11
Leverage
Majority of the Plants show Poor Leverage Performance:
8 Plants have shown below average target achievement on YTD basis ranging from 2% (Chaibasa) to 40% (Jamul)
Majority of the Plants show Poor Leverage Performance:
Except for Disha and Svalamban where the Leverage performance on YTD basis a on May 2017 is above 90%, the remaining sectors have leverage performance range from low to average. S.Paryavaran, Leisa, Vidya Utkarsh and S.Swacchata are a particular cause for concern in terms of Leverage traction achieved.
Leverage Ratio (%age of ACC share leveraged) across the board has been poor, except for Svalambhan and Arogyam.

## Slide 12
Plant | Target Beneficiary (YTY) | Target Beneficiary (YTD) | Actual Beneficiary (YTD) | Beneficiary Achieved |  | Cost/Beneficiary | 
 |  |  |  | (YTY) | (YTD) | (YTY) | (YTD)
Tikaria | 9,732 | 4,223 | 914 | 9% | 22% | 1,734 | 2,781
Kymore | 34,072 | 17,455 | 5,739 | 17% | 33% | 451 | 199
Damodhar | 12,828 | 7,481 | 3,800 | 30% | 51% | 295 | 266
Bargarh | 16,312 | 7,495 | 4,605 | 28% | 61% | 1,106 | 722
Kudithini | 21,455 | 15,770 | 11,889 | 55% | 75% | 353 | 88
Chaibasa | 24,142 | 10,318 | 7,899 | 33% | 77% | 443 | 656
Gagal | 39,141 | 26,214 | 21,783 | 56% | 83% | 455 | 266
Wadi | 6,638 | 2,570 | 2,201 | 33% | 83% | 1,470 | 1,198
Sindri | 24,301 | 12,660 | 13,354 | 55% | 105% | 776 | 264
Thondebhavi | 7,251 | 4,560 | 5,283 | 73% | 116% | 498 | 187
Jamul | 1,687 | 1,687 | 2,187 | 130% | 130% | 10,580 | 3,993
Lakheri | 7,002 | 4,540 | 6,706 | 96% | 148% | 1,114 | 272
Chanda | 10,679 | 3,944 | 5,996 | 56% | 152% | 1,106 | 546
Madukkarai | 272,560 | 100,980 | 155,999 | 57% | 154% | 53 | 24
Total | 487,800 | 219,897 | 248,355 |  |  |  | 
Beneficiary by Plant
LOW
AVERAGE
GOOD
OVER ACHIEVER

## Slide 13
Vertical | Target Beneficiary(YTY) | Target Beneficiary (YTD) | Actual Beneficiary (YTD) | Beneficiary Achieved |  | Cost/Beneficiary | 
 |  |  |  | (YTY) | (YTD) | (YTY) | (YTD)
Vidya Saarthi | 102 | 0 | 0 | 0% | null | 33,137 | null
NGO admin /others | 1,353 | 932 | 26 | 2% | 3% | 5,216 | 51,974
# Save Kids Life | 3,980 | 1,360 | 490 | 12% | 36% | 88 | 124
Leisa | 156,626 | 3,996 | 1,258 | 1% | 31% | 66 | 2,458
Disha | 5,763 | 2,986 | 1,613 | 28% | 52% | 3,926 | 5,597
Dhrona | 10,428 | 5,956 | 5,052 | 48% | 85% | 573 | 174
Swavlamban | 20,812 | 7,896 | 8,815 | 42% | 112% | 948 | 705
Vidya Utkarsh | 32,060 | 15,811 | 12,700 | 40% | 80% | 1,007 | 626
S.Swacchata | 47,114 | 35,686 | 21,256 | 45% | 60% | 629 | 331
Arogyam | 85,677 | 34,734 | 36,620 | 43% | 105% | 246 | 106
S.Paryavaran | 123,885 | 110,540 | 160,525 | 130% | 145% | 175 | 33
Total | 487800 | 219897 | 248355 |  |  |  | 
Beneficiary by Sector

## Slide 14
Beneficiary
Majority of the Plants show high achievement in beneficiary coverage:
Except for Tikaria and Kymore, the remaining Plants have performed well. 4 plants have returned average to good performance and 6 plants have over achieved (i.e. surpassed the YTD beneficiary targets)
Cost per beneficiary remains high for Tikaria, Jamul and Wali. Kymore, Kudithini, Thondebhavi and Madukarrai have very competitive cost/beneficary ratio.
In some of the key sectors beneficiary achievement is poor:
For # Savekidslife, LEISA and Disha, only 50% of the beneficiary targets have been achieved and a close monitoring of the coverage is in order.
Note:
The correlation between spending and beneficiary coverage is low.
Also it is critical to asses for double counting of beneficiaries and also attributing beneficiary numbers for capital intensive projects.

## Slide 15
Thank You
The MPR Dashboard is available at
https://datastudio.google.com/u/0/org//reporting/0B9KpuN-Luu2gZGd4cWJzV0xjUjQ/page/QM0E